# Quotation

## Online pharmacy ordering and fulfilment platform

| Field | Value |
| --- | --- |
| Quotation ID | SAL-PHARM-QT-001 |
| Date | 17 September 2026 |
| Valid until | 17 October 2026 |
| Prepared by | Salanor Ltd, Kigali, Rwanda |
| Scope reference | [PHARMACY-ONLINE-PLATFORM-SRS.md](./PHARMACY-ONLINE-PLATFORM-SRS.md) (SAL-PHARM-SRS-001 v2.0) |
| Currency | Rwandan Francs (RWF), exclusive of any applicable taxes |

## 1. Summary

This quote covers design, build, integration, testing support, and initial go-live for the platform described in SAL-PHARM-SRS-001. That document is the functional baseline: what we build matches the SRS unless you request a written change order.

Total fixed price (full SRS scope): 5,400,000 RWF

Estimated calendar duration: 16 to 22 weeks from contract signing and receipt of deposit, assuming workshop items in SRS section 24 are resolved within the first three weeks and the pharmacy’s PMS vendor provides integration access within a reasonable time.

This is not a brochure site or a WhatsApp-only ordering form. It is a regulated retail channel with prescription review, PMS alignment, and insurance-ready checkout.

## 2. What is included

| Deliverable | Maps to SRS |
| --- | --- |
| Public pharmacy site (legal disclosures, catalog, search, EN/FR UI) | Sections 4, 5, 6 |
| Patient accounts, addresses, consent and privacy flows | Sections 6, 4.3 |
| Cart and checkout (OTC and Rx rules, branch selection) | Section 7 |
| Prescription upload, pharmacist review queue, checklist, rejection codes | Sections 8, 9, Appendices A and C |
| Order lifecycle and staff console (roles per section 5) | Sections 9, 10 |
| Pickup codes and delivery workflow (zones configured with you) | Section 11 |
| Payments: mobile money and pay-at-pickup/co-pay flows as agreed in workshop | Section 12 |
| Insurance context (RSSB and other schemes as data you provide; formulary warnings) | Section 13 |
| PMS integration: catalog sync, reservation, sale reconciliation (one PMS product) | Section 14 |
| Notifications (SMS and/or email; WhatsApp if provider account is yours) | Section 15 |
| Returns, cancellations, complaints | Section 16 |
| Reporting and exports (Rx log, register export, insurance pending, audit) | Section 17 |
| Multi-branch data model (one branch live; second branch config if same PMS) | Section 18 |
| Security and operational behaviour per NFRs | Section 19 |
| UAT support against acceptance criteria (section 22) | Section 22 |
| Production deployment, SSL, backup configuration | NFR-09 |
| Two on-site or video training sessions for pharmacist and counter staff |  |
| 30 days post go-live defect fix period (bugs against SRS, not new features) |  |

## 3. What is not included

| Item | Notes |
| --- | --- |
| Rwanda FDA online pharmacy authorization fees and legal advice | Pharmacy responsibility |
| PMS license fees, RSSB contracts, payment aggregator merchant fees | Pharmacy contracts |
| SMS, WhatsApp, maps, or payment gateway transaction charges | Billed by providers to pharmacy |
| Ongoing hosting and support after the defect-fix period | See section 7 (optional retainer) |
| Native iOS/Android apps | Out of scope in SRS; can be quoted separately |
| Second PMS integration or major PMS change mid-project | Change order |
| Content writing beyond structure (long-form medical copy, full Kinyarwanda translation) | Client or separate copy quote |
| Hardware (tablets for delivery, printers) | Client |

If the chosen PMS has no API and only manual export/import is possible, we will agree a reduced integration scope in writing during week 1. That may lower price (manual sync SOP) or require a change order if the pharmacy insists on real-time sync without vendor cooperation.

## 4. Price breakdown (full scope)

Transparent allocation for your records. Invoicing follows section 5, not line-by-line.

| Component | RWF |
| --- | --- |
| Discovery, information architecture, UI for patient and staff | 900,000 |
| Catalog, search, stock-aware behaviour (PMS-driven) | 650,000 |
| Accounts, cart, checkout, order state machine | 850,000 |
| Prescription intake, pharmacist workflow, audit trail | 1,350,000 |
| PMS integration (single vendor, bidirectional as per SRS 14) | 950,000 |
| Insurance and co-pay flows, reporting | 650,000 |
| Delivery, notifications, returns and complaints | 450,000 |
| UAT, deployment, training, 30-day defect period | 600,000 |
| Total | 5,400,000 |

## 5. Payment schedule (recommended)

Fixed-price work for a small business is often paid in milestones, not 100% upfront. A deposit plus balance at acceptance plus short installments after go-live is normal in Rwanda and internationally, provided it is in a signed agreement with clear dates and deliverables.

Proposed schedule for 5,400,000 RWF:

| Milestone | % | Amount (RWF) | Trigger |
| --- | --- | --- | --- |
| 1. Project start | 30% | 1,620,000 | Signed agreement and invoice; deposit received before development starts |
| 2. UAT acceptance | 30% | 1,620,000 | Staging environment passes SRS section 22 UAT with your responsible pharmacist (or delegated tester) |
| 3. Go-live | 15% | 810,000 | Production launch and handover of admin access |
| 4. Installment 1 | 8.33% | 450,000 | Due 30 days after go-live |
| 5. Installment 2 | 8.33% | 450,000 | Due 60 days after go-live |
| 6. Installment 3 | 8.34% | 450,000 | Due 90 days after go-live |

Total | 100% | 5,400,000 |

Notes:

Installments are interest-free; they are a cash-flow convenience, not a loan product.

If you prefer no installments, milestones 1 to 3 can be 40% / 40% / 20% with the final 20% at go-live.

Late payment: work pauses, hosting and support suspend after 15 calendar days past due date until account is current (standard B2B clause).

Intellectual property and production credentials: full transfer of custom code and deployment documentation upon receipt of final payment, unless we agree earlier transfer with a retained license clause for generic components. State this explicitly in the contract.

Is this unprofessional? No, if you present it as a milestone payment schedule on letterhead with invoices, not as an informal “pay me when you can.” What sounds unprofessional is vague amounts, no written scope, or building the entire system before any deposit. Do not accept 800,000 RWF for this scope; that figure is unrelated to this quote (see section 8).

## 6. Timeline (indicative)

| Phase | Weeks | Output |
| --- | --- | --- |
| Workshop and PMS access | 1 to 3 | Signed integration approach, configs |
| Patient site and OTC path | 4 to 8 | Staging: browse, cart, pay or pay-at-pickup |
| Rx and pharmacist console | 9 to 14 | Staging: full Rx scenarios |
| Insurance and reports | 15 to 17 | Staging: co-pay and exports |
| UAT and go-live | 18 to 22 | Production per section 22 |

Delays caused by missing PMS API, unpaid third-party accounts, or FDA authorization not in place extend the timeline without automatic price reduction.

## 7. Optional ongoing services (after go-live)

| Service | Monthly (RWF) | Includes |
| --- | --- | --- |
| Care plan | 320,000 | Managed hosting, TLS, backups, monitoring, up to 4 hours minor fixes or config |
| Care plus | 480,000 | Above plus priority response, monthly sync health review, security patches |

Not mandatory to sign on day one, but production systems handling health data should not run without maintenance. Quote hosting separately if you host elsewhere.

## 8. Alternative if budget is constrained (not full SRS)

If 5,400,000 RWF is not feasible, do not pretend the full SRS is included. Offer a written phase instead:

| Option | Scope (summary) | Price (RWF) | Duration |
| --- | --- | --- | --- |
| Phase 0 | Professional site, OTC catalog (manual or simple stock), order request (form/WhatsApp handoff), legal pages | 950,000 | 4 to 6 weeks |
| Phase 1 | Phase 0 plus patient accounts, cart, MoMo or pay-at-pickup, staff order list (no full Rx engine) | 2,450,000 cumulative | +8 to 10 weeks |
| Phase 2 | Full Rx workflow and pharmacist console (SRS sections 8 to 9) | +1,850,000 | +6 to 8 weeks |
| Phase 3 | PMS integration plus insurance plus delivery plus reporting (remainder of SRS) | +1,100,000 | +6 to 8 weeks |

Phase 0 to 3 total aligns with full SRS (~5,400,000) but lets her stop after any phase with a working product.

Her 800,000 RWF expectation matches roughly Phase 0 minus (brochure plus catalog only, no proper checkout). You can counter with 950,000 RWF for Phase 0 as the floor for something you can stand behind, or decline if she insists on “full platform” at that price.

## 9. Realistic view for both sides

For the pharmacy

They gain a sales channel that respects GDP/GPP and FDA online rules, tied to stock and receipts they already need for RRA and RSSB.

They must still fund PMS, authorization, and payment merchant costs.

They must assign a responsible pharmacist for UAT and ongoing Rx decisions; software does not remove liability.

For Salanor (you)

5.4M RWF over ~5 months is ~1.08M per month gross before tax, tools, and any subcontract (PMS specialist, designer). That is fair for one senior lead plus part-time help, not a large agency bench.

PMS integration risk is the main unknown: price assumes one cooperative integration; document that in the contract.

Do not start work without deposit; do not go-live without UAT sign-off and at least go-live milestone paid.

Negotiation

You may reduce price only by reducing scope (phases, manual PMS sync, insurance deferred to Phase 3), not by keeping SRS and cutting price.

Installments after go-live are a sales tool for a serious client with cash-flow timing issues, not for a client who cannot afford the project.

## 10. Acceptance

To proceed:

Confirm acceptance of SAL-PHARM-SRS-001 v2.0 as functional scope (or list written exceptions).

Complete workshop items in SRS section 24 within three weeks of signing.

Sign the service agreement [PHARMACY-ONLINE-PLATFORM-SOW.md](./PHARMACY-ONLINE-PLATFORM-SOW.md) (SAL-PHARM-SOW-001), which incorporates this quotation and the SRS.

Pay milestone 1.

Client name: _______________________________

Signature / date: _______________________________

Salanor Ltd

Authorized signatory: _______________________________

Date: _______________________________

*This quotation is an offer to contract. It is not legal or tax advice. VAT or withholding, if applicable, will be shown on invoices per Rwanda law.*